## Project Status
Area | Item | Status | Details
Docs | PRD v3.0 (45 sections) | DONE | Single source of truth
Docs | Architecture / DB / API docs | DONE | Design level, not code
Docs | 100-Sprint plan (markdown) | DONE | docs/09_Sprints/README.md
Code | workers/crawler skeleton (build+run) | DONE | Builds, runs, full pipeline works
Code | S021 resilient fetch (TLS/timeout/retry) | DONE | ibps rescued 0->21; 4/10 sources now yield data
Code | S022 fix/verify source URLs | PENDING | drdo & rrb-ald = 404; 3 railway/bpsc unreachable
Code | S023 relevance/keyword tuning | PENDING | Still pulling nav/result links, not only jobs
Code | S024 opportunity-type classification | PENDING | Everything tagged 'job'
Code | S025 JS-rendered sources (SSC) | PENDING | Needs headless fetch
Code | S026 railway federation | PENDING | rrb/rrc unreachable from here
Code | S030 Postgres store | PENDING | Currently JSON file
Code | Backend API | PENDING | services/ empty
Code | Frontend app | PENDING | apps/ empty
Code | Auth / Profile / Search / AI | PENDING | S011-S050

## Crawler 10 Sources
Source ID | Organization | Sector | Result after S021 | Candidates | Remaining issue | Next sprint
upsc | Union Public Service Commission | central | WORKS | 20 | Pulls nav/results too | S023/S024
uppsc | UP Public Service Commission | state | WORKS | 32 | Pulls advt+nav | S023
ibps | Inst. of Banking Personnel Sel. | banking | WORKS (fixed) | 21 | Was TLS-broken; now OK | S023
sbi | State Bank of India (careers) | banking | WORKS | 4 | Verify links are real | S023
ssc | Staff Selection Commission | central | 0 candidates | 0 | JavaScript-rendered list | S025
drdo | DRDO careers | research | HTTP 404 | 0 | Wrong URL path | S022
rrb-ald | RRB Prayagraj | railway | HTTP 404 | 0 | Wrong URL path | S022/S026
rrb-cdg | RRB Chandigarh | railway | TIMEOUT | 0 | Unreachable from here (URL/geo/down) | S022/S026
rrc-ner | Railway Recruitment Cell | railway | FETCH FAIL | 0 | Unreachable from here | S022/S026
bpsc | Bihar Public Service Commission | state | TIMEOUT | 0 | Unreachable from here | S022

## Crawler Plan S021-S030
Sprint | Objective | Acceptance criteria | Status | Group
S021 | Robust fetch (timeout/retry/TLS) | >=8/10 sources fetch without a code-level error | DONE | MVP-crawler
S022 | Fix & verify source URLs | Every listingUrl returns 200 & shows notices in browser | NEXT | MVP-crawler
S023 | Relevance / keyword tuning | ≥80% captured candidates are real recruitment notices | PENDING | MVP-crawler
S024 | Opportunity-type classification | Each candidate tagged job/result/admit/answer-key | PENDING | MVP-crawler
S025 | JS-rendered sources (SSC) | SSC returns >0 real notices | PENDING | MVP-crawler
S026 | Railway federation | ≥2 railway sources yield notices | PENDING | MVP-crawler
S027 | Detail-page enrichment (dates/vacancies) | Opportunities carry closeDate where stated | PENDING | Deepen
S028 | Semantic dedup across sources | Cross-source duplicate collapses to 1 | PENDING | Deepen
S029 | Source health + run report | 'sources' shows per-source health | PENDING | Deepen
S030 | Persist to Postgres | Full pipeline runs on Postgres, same interface | PENDING | Deepen