## 100 Sprint Status
Sprint | Phase | Objective | PRD Sec | Depends On | Status
S001 | Foundation | Repo + folder structure + tooling | 44 | - | DONE
S002 | Foundation | Master PRD v3.0 | all | S001 | DONE
S003 | Foundation | Domain model & canonical entities | 7 | S002 | DONE
S004 | Foundation | Source Registry design + Data Engine PRD | 26 | S003 | DONE
S005 | Foundation | Roadmap + 100-sprint plan | 39 | S004 | DONE
S006 | Architecture | System & application architecture docs | 2 | S005 | DESIGN-DONE
S007 | Architecture | Database schema per bounded context | 4 | S006 | DESIGN-DONE
S008 | Architecture | API standards & contracts | 5 | S007 | DESIGN-DONE
S009 | Architecture | ADRs (uuidv7, encryption, money, schema) | 10 | S008 | DESIGN-DONE
S010 | Architecture | Monorepo bootstrap: apps/services/packages, CI | 44 | S009 | PENDING
S011 | Core Platform | Postgres + migrations + base schema | 4 | S010 | PENDING
S012 | Core Platform | Auth service (signup/login, sessions, OTP) | 33 | S011 | PENDING
S013 | Core Platform | RBAC + roles | 33 | S012 | PENDING
S014 | Core Platform | Aspirant Profile service | 17 | S013 | PENDING
S015 | Core Platform | Entities: Organizations, Departments + seed | 7 | S011 | PENDING
S016 | Core Platform | Entities: Exams, Qualifications + seed | 7 | S015 | PENDING
S017 | Core Platform | Skill taxonomy (versioned) + cyber seed | 12.1 | S016 | PENDING
S018 | Core Platform | Consent management + audit-log foundation | 34 | S013 | PENDING
S019 | Core Platform | Document Vault foundation (encrypted) | 20 | S018 | PENDING
S020 | Core Platform | API gateway + shared packages | 5 | S011 | PENDING
S021 | Data Engine | Resilient fetch (timeout/retry/TLS) | 25 | - | DONE
S022 | Data Engine | Fix/verify source URLs (cyber recovered) | 26 | S021 | DONE
S023 | Data Engine | Relevance filter (drop nav/product noise) | 25 | S022 | DONE
S024 | Data Engine | Opportunity-type classification | 9 | S023 | DONE
S025 | Data Engine | JS-rendered sources - headless (CERT-In,NIC,SSC) | 25 | S024 | NEXT
S026 | Data Engine | Expand coverage: railway federation + sources | 26 | S025 | PENDING
S027 | Data Engine | Detail-page extraction (dates/vacancies) + confidence | 25 | S026 | PENDING
S028 | Data Engine | Entity resolution + semantic dedup | 7 | S027;S016 | PENDING
S029 | Data Engine | Source health monitoring + run reports | 26 | S027 | PENDING
S030 | Data Engine | Postgres store + history/trends capture | 11 | S028;S011 | PENDING
S031 | Jobs & Search | Opportunity domain service + facet model | 9 | S030 | PENDING
S032 | Jobs & Search | Data-Engine->Platform publish seam | 25 | S031 | PENDING
S033 | Jobs & Search | Opportunity detail API + SSR page | 8 | S032 | PENDING
S034 | Jobs & Search | Search index + 18 facets | 18.1 | S032 | PENDING
S035 | Jobs & Search | Structured search API + filters UI | 18 | S034 | PENDING
S036 | Jobs & Search | Ranking v1 (relevance/eligibility/freshness) | 18.2 | S035 | PENDING
S037 | Jobs & Search | AI Smart Search (NL -> facets) | 18.3 | S036;S044 | PENDING
S038 | Jobs & Search | Profile pages: Organization + Exam (SEO) | 8 | S033 | PENDING
S039 | Jobs & Search | Profile pages: Qualification + Skill | 8 | S038;S017 | PENDING
S040 | Jobs & Search | SEO infra: SSR, structured data, sitemaps | 31 | S038 | PENDING
S041 | AI & Profile | Intelligent Profile completion + signals | 17 | S014 | PENDING
S042 | AI & Profile | AI Eligibility Checker (deterministic) | 15 | S041;S016 | PENDING
S043 | AI & Profile | Skills Engine: Skill/Profile Match scoring | 12 | S017;S042 | PENDING
S044 | AI & Profile | AI governance: registry, prompts, grounding gate | 16 | S020 | PENDING
S045 | AI & Profile | AI Resume Parser + PII handling | 15 | S044;S019 | PENDING
S046 | AI & Profile | Career DNA Engine v1 | 13 | S043;S045 | PENDING
S047 | AI & Profile | AI Personalized Recommendations | 15 | S046 | PENDING
S048 | AI & Profile | AI Skill Gap + Certification recs | 12.4 | S043 | PENDING
S049 | AI & Profile | Career Paths + Learning Roadmaps | 14 | S048 | PENDING
S050 | AI & Profile | AI eval harness + hallucination guardrails | 16 | S044 | PENDING
S051 | Applications | Saved Jobs | 20 | S033 | PENDING
S052 | Applications | Application Tracker + stages | 20 | S051 | PENDING
S053 | Applications | Exam Calendar + personalization | 9.5 | S033 | PENDING
S054 | Applications | Notifications infra (in-app/push/email) | 19 | S014 | PENDING
S055 | Applications | Notif preferences + anti-fatigue + re-notify | 19 | S054 | PENDING
S056 | Applications | SMS channel + result-day surge | 19 | S055 | PENDING
S057 | Applications | Document Vault full (reuse/log/retention) | 20 | S019 | PENDING
S058 | Applications | AI Resume Builder | 15 | S045 | PENDING
S059 | Applications | Form Filling - aspirant flow + lifecycle | 21 | S057 | PENDING
S060 | Applications | Form Filling - executive + fraud/refund/SLA | 21.3 | S059;S066 | PENDING
S061 | Admin & Ops | Reviewer panel UI (gate at scale) | 27 | S030 | PENDING
S062 | Admin & Ops | Admin panel (sources/entities/users/flags) | 27 | S013 | PENDING
S063 | Admin & Ops | Support workflow + ticketing | 27 | S062 | PENDING
S064 | Admin & Ops | Escalation / Grievance workflow | 27 | S063 | PENDING
S065 | Admin & Ops | Moderation, takedown + correction propagation | 27 | S061 | PENDING
S066 | Admin & Ops | Fraud detection & Trust & Safety | 28 | S030 | PENDING
S067 | Admin & Ops | Analytics event taxonomy + product analytics | 29 | S010 | PENDING
S068 | Admin & Ops | A/B experimentation + metric governance | 29 | S067 | PENDING
S069 | Admin & Ops | Feedback system + ratings | 29 | S067 | PENDING
S070 | Admin & Ops | Incident/on-call + runbooks | 27 | S062 | PENDING
S071 | Growth & Monetization | Premium tier + subscription | 30 | S014 | PENDING
S072 | Growth & Monetization | Payments integration | 30 | S071 | PENDING
S073 | Growth & Monetization | Freemium gating (no pay-to-rank) | 30.2 | S072 | PENDING
S074 | Growth & Monetization | Referral + shareable Career DNA cards | 31.2 | S046 | PENDING
S075 | Growth & Monetization | Retention loops (streaks/progress/alerts) | 31.3 | S054 | PENDING
S076 | Growth & Monetization | Government Schemes module | 22 | S030 | PENDING
S077 | Growth & Monetization | Government Career News module | 23 | S030 | PENDING
S078 | Growth & Monetization | B2B / Institutional analytics (early) | 30 | S067 | PENDING
S079 | Growth & Monetization | Ecosystem referrals (certifications) | 30 | S048 | PENDING
S080 | Growth & Monetization | Ads (guardrailed, labeled) | 30 | S073 | PENDING
S081 | Scale & Quality | Performance: caching, p95, CDN | 35 | S033 | PENDING
S082 | Scale & Quality | Search scale + ranking quality loop | 18 | S036;S068 | PENDING
S083 | Scale & Quality | Security hardening + pen test + review gates | 33 | S012 | PENDING
S084 | Scale & Quality | Privacy/DPDP: rights, retention automation | 34 | S018 | PENDING
S085 | Scale & Quality | Field-level encryption for sensitive PII | 33 | S019 | PENDING
S086 | Scale & Quality | Observability: metrics/traces/logs/dashboards | 35 | S010 | PENDING
S087 | Scale & Quality | Testing: unit/integration/e2e + golden sets | 16 | S050 | PENDING
S088 | Scale & Quality | Accessibility WCAG 2.1 AA audit | 38 | S035 | PENDING
S089 | Scale & Quality | Internationalization: Hindi + regional | 37 | S033 | PENDING
S090 | Scale & Quality | Cost controls: per-user + AI/OCR/SMS budgets | 40 | S086 | PENDING
S091 | Launch & Future | Production deployment + infra-as-code | 10 | S083 | PENDING
S092 | Launch & Future | Disaster recovery + backup + RTO/RPO | 36 | S091 | PENDING
S093 | Launch & Future | Observability & alerting productionization | 35 | S086 | PENDING
S094 | Launch & Future | Cost optimization pass | 30.3 | S090 | PENDING
S095 | Launch & Future | Beta launch (limited cohort) | 39 | S092 | PENDING
S096 | Launch & Future | Bug bash + hardening | 39 | S095 | PENDING
S097 | Launch & Future | Public launch | 39 | S096 | PENDING
S098 | Launch & Future | Post-launch analytics + iteration | 40 | S097 | PENDING
S099 | Launch & Future | Roadmap v2 planning | 39 | S098 | PENDING
S100 | Launch & Future | Retrospective + v2 kickoff | 39 | S099 | PENDING

## Summary
Status | Count
DONE | 9
DESIGN-DONE | 4
NEXT | 1
PENDING | 86
TOTAL | 100